## Sheet1
Current Status | Tender Ref. No. / NIT & Date | Tender fee Online /Exempted as per MSME bidder | EMD /Exempted as per MSME bidder | EMD /online payment received status | Bank Name's | Job Allocation No. (JAN) | Previous EIC at Aakar | Current EIC at Aakar | Client Name | State | Place / City | Name of Work | PO/WO/LOA Details | Financial Year | PO/WO/LOA Date | Work Start Date | Completion Date as per LOA/PO | Latest Work Completion Date (as per Time Extension) | Completion Date as per Finla Time Extension / Deviation | Client Billing Address | Name of Authorised Person At Client (Previous) | Name of Authorised Person At Client (Current) | Designation of Authorised Person At Client (Previous) | Designation of Authorised Person At Client (Current) | Mobile No. of Authorised Person At Client (Previous) | Mobile No. of Authorised Person At Client (Current) | Email of Authorised Person At Client | Email CC (Client)/C&M | Contract Value Version as per LOI/NOA/LOA/DLOA/PO GST Extra | GST Extra /Including | Updated Contract Value GST Extra | Bank Guarantee Submitted / CPG Not Submitted | Bank Guarantee Value | Bank Guaratee Expiry Date | Bank Guaratee Expiry Date (Claim) | Client WO/PO Upload LINK | Client contract agreement LINK | 1st Sub Contractor's Name | Proprietor / Auth. Signatory of Sub-Cont. | Mobile No. of Sub-Cont. Proprietor / Auth. Signatory's | Email of Sub-Cont. Proprietor / Auth. Signatory's | GSTIN of Sub Contractor | WO on % Party | Work Order No. | Work Order Date | Sub-Contractor Work Order (Upload) | C&M E-Mail ID | C&M Mobile No | PO Issued Concerned Person | Work Start Date as per PO | Actual work start Date as per site Conditions
Payment Pending | NTECL/C&M/NIT-143/CS-2726 | Exempted | EMD - BG Form | received | SBI | 10005 | Manpreet Kaur | Monika Kochhar | NTPC | Tamil Nadu | Chennai | PCC Paving between Track Hopper I & II at Barh STPP. | LOA No.: NTECL/C&M/NIT-143/CS-2726 / LOA-2749 dated 11/10/2017 | 2017-18 | 2017-10-11 | 2017-10-11 | 2018-06-11 | 2025-10-15 | NIL | NTPC Tamilnadu Energy Company Ltd. Vallur Thermal Power Project, Vellivoyal Chavadi Post, Ponneri Taluk, Thiruvallur District Chennai | Shri P.P. Jayachandran | Sh. Vidhya Bhushan Kumar | Manager | Deputy Manager | 8826697153 | 9948044458 | VBkumar01@ntpc.co.in | parul@ntpc.co.in | 52231592 | 18% | NIL | BG Submitted | ₹ 2,59,620.00 | 2026-07-06 | 2026-06-15 | https://drive.google.com/file/d/1gTnQD5_vaiDYrrKIKyX1tac-3VSji1c_/view?usp=sharing | https://drive.google.com/file/d/1Nw5-gDoVvo37929E4uFaoLhYZ-GFaDf0/view?usp=sharing | Araan Constructions | Arun Kumar MS | 9445976751 | araanconstructions@yahoo.com | 33AMDPA5733F1ZM | 0.07 | 10005/12220058 | 2022-04-05 | https://drive.google.com/file/d/1Uoles7nM3GO1azbccZT0KSQQ_aLxRx4n/view?usp=sharing | manager.cst@railway.com | 91 9153217419 | Mr. MOHAMMAD FAIJAN | 2025-01-18 | 2025-07-25
Ongoing | NIT / Spec. Ref. No. RPT-HVDC/C&M/WC-135/NIT-016(E)/2021, RFX 5002001670 | Tender fee online 2655/- | Exempted as per MSME bidder | Not received | HDFC | 10053 | Manpreet Kaur | IRAM | PGCIL | Kerala | Thrissur | Construction of Community Centre at Thrissur. | LOA No. RPT/HVDC/C&M/WC-135/LOA-241 Dt. 11/5/2021 SAP.O. Number : 6900010896 | 2021-22 | 2021-05-11 | 2020-03-21 | 2021-12-08 | 2025-10-31 | 2026-12-31 | POWER GRID CORPORATION OF INDIA LTD ±320KV, HVDC Terminal Station, KAU Campus, Vellanikara Post, Thrissur, Kerala | Manoj Kumar | Shri P.P. Jayachandran | Deputy Manager | Deputy General Manager | 9948044458 | 9074356272 | hvdc.thrissur@powergrid.co.in | supriya_tv@powergrid.in | 30933410 | 18% | 34032723 | CPG Not Submitted | N/A | N/A | N/A | https://drive.google.com/drive/folders/18OWnUOZ23EwaI3ikyCOf4Xst4pk7jirT?usp=sharing; https://drive.google.com/file/d/1HoCZ7xAgmBc80YKaoblGUdUpkVeT7fqb/view?usp=sharing | https://drive.google.com/file/d/1Ep4yaLlJps1WK_MjZ6JBLKvG8I1cUNBn/view?usp=sharing | M/s COCHIN ENGINEERING PROJECT INDIA PRIVATE LIMITED | Shri Umesh Manickan SALEENA UMESH | 8129797634 | rishikeshr349@gmail.com | 32DRQPR8682K1ZS | 11.5 | 12220060 | 2022-05-14 | https://drive.google.com/file/d/1ct-6eDqCZdIy_MK4Lq-_lLIepRnndS6S/view?usp=sharing | sanvithareddy2017@gmail.com | 89430 31000 | Mr. FAKHRUL HASAN | 2025-06-18 | 2025-07-09
Payment Pending | Tender Reference Number NTPC/KBUNL/9900223549 Tender ID 2021_KBUNL_52938_1 | Tender fee online 2000/- | EMD - BG Form | received | Axixs | 10071 | Manpreet Kaur | Monika Kochhar | NTPC | Bihar | Kanti | Construction of drains all around Coal Stock Pile, Coal slurry settling pond system, Coal Decanted Sump & Pump House at CHP Area at KBUNL, Kanti. | Purchase Order No. : 4200057197-026-1087 Date : 13.09.2022 ( version : 1 Date : 19.11.2022 ) KBUNL (Purchase Order No. : 5500039539-026-2040 Date : 31.12.2021 Ref. No.: LOI - 2040-026-9900223549 Date: 14.12.2021 | 2021-22 | 2021-01-01 | 2022-01-01 | 2022-09-30 | 2025-12-15 | NIL | NTPC Limited 1087 Muzaffarpur Thermal Power Station PO Kanti, Distt. Muzaffarpur Muzaffarpur Bihar-843130,India | V K JAISWAL | V K JAISWAL | The HOD O&M Civil | DGM(CCD) Sr. Manager | 7319941705 | 9445002541 | VKJAISWAL03@NTPC.CO.IN; | dipakkumarchaki@ntpc.co.in | 14361586.09 | 18% | 17893493.04 | BG Submitted | 3082247 | 2027-08-15 | 2027-05-15 | https://drive.google.com/file/d/1DyfD8FX1Dl4yTv2fBhcP8bHIKhwyxipg/view?usp=sharing | https://drive.google.com/file/d/1Nw5-gDoVvo37929E4uFaoLhYZ-GFaDf0/view?usp=sharing | M/s KABIR INFRA | Mr. FAKHRUL HASAN | 8757375705 | fakhrulhasancv428@gmail.com; | 10ABCFK4223G1Z0 | 0.05 | 12520011 | 2025-07-19 | mail at 19-09-2025 | heavensgarden10@gmail.com | 9412203436 | Mr. UmeshM Manickan | 2024-10-01 | 2025-08-20
Ongoing | Tender Reference Number NTPC/USSC-CPG1/9900227744 Tender ID 2021_NTPC_55729_1 | Exempted | EMD - DD Form | Not received | Canra | 10080 | Sheeba | Monika Kochhar | `NTPC | Odisha | Darlipalli | Construction of Two Nos. of Seepage Water Pump House at Ash Dyke Area at NTPC Darlipalli | Purchase Order No. : 5500040068-025-1041 Date : 04.03.2022 | 2022-23 | 2022-03-04 | 2022-03-21 | 2023-09-20 | 2025-12-15 | NIL | NTPC Limited 1053 Darlipali STPP P.O. Darlipali Odisha Sundargarh Odisha-770072, India | Sh S. B. MANDAL | Sh S. B. MANDA | Sr. Manager | EIC. AGM Civil const / AGM Civil Const | 9471001383 | 9404951638 | sbmandal@ntpc.co.in | PRISHANTPATHIK@NTPC.CO.IN | 14439617.32 | 18% | 17705857.12 | CPG Not Submitted | N/A | N/A | N/A | https://drive.google.com/file/d/1kbBtN OJ6eEvzrm94XFBoPEfmZivqy xyb/view?usp=sharing | https://drive.google.com/file/d/1kENFWDaXKPmVaD8ENy1IjksZnlnqFOkx/view?usp=sharing | M/s GANESH SHARMA CONSTRUCTION | GANESH SHARMA | 8435422224 | gsharma2060@yahoo.com | 21BIDPS4583E1ZC | 0.04 | 03-10080-12520009 | 2025-07-08 | mail on 20-08-2025 | pcarajeev@gmail.com | 9494141498 | Ms. Sangana Praveena | 2025-01-23 | 2025-05-10
Ongoing | Tender Reference Number NTPC/USSC-CPG1/9900235227 Tender ID 2022_NTPC_60692_1 | Tender fee online 5000/- | EMD - BG Form | Not received | ICICI | 10098 | Manpreet Kaur | Monika Kochhar | NTPC | Karnataka | Kudgi | Construction of RCC Culvert, Patrolling road and Diversion of BoundaryWall on west side of Plant Boundary at Kudgi STPP | Purchase Order No. : 5500041039-025-1041 Date : 29.07.2022 Purchase Order No. : 5500041039-025-1041 Date : 29.07.2022 ( version : 1 Date : 24.02.2025 ) | 2022-23 | 2022-07-29 | 2022-08-30 | 2023-05-29 | 2025-09-30 | NIL | NTPC Limited 1046 Kudgi Super Thermal Power Project BASAVANA BAGEWADI, BIJAPUR Karnataka-586121, India | Pankaj Kumar Gupta | Manoj Kumar | Manager | Sr. Manager DGM (CCD) | 9424209153 | 9420491809 | tmanojkumar@ntpc.co.in | saketsrivastava@ntpc.co.in | 16944108.5 | 18% | NIL | BG Submitted | 3082767 | 2026-09-15 | 2026-06-15 | https://drive.google.com/file/d/1QGzHprylti-b1I12xh-7M0qu-y680IkG/view?usp=sharing | https://drive.google.com/file/d/1ckMbKpLvqmZywNaPo7fpAzzvSo6n0JiU/view?usp=sharing | National Technology & Construction Company | Yashpal Rana | +917090998906 | ysrana.aiepl@gmail.com | 29BKHPR0813G3Z2 | 0.07 | 12220077 | 2022-08-08 | https://drive.google.com/file/d/1CXdjcxE66Vl49X3pF8xz8jf4-jaLZsN8/view?usp=sharing | ysrana.aiepl@gmail.com | 8435422224 | Mr. FAKHRUL HASAN | 2024-10-04 | 2025-05-10
Payment Pending | SPECIFICATION NO. : WR2/NT/CIVIL/DOM/G01/22/00048, RFX NO : 5002002426 | Tender fee online 2500/- | Exempted as per MSME bidder | Not received | Canra | 10108 | Manpreet Kaur | IRAM | PGCIL | Gujarat | Banaskantha | Balance Works for Construction of Store Shed at 400/220 kV Banaskantha (Radhanesda) GIS Pooling Substation. | BLOA Ref. No. WR-II/C&M/SD/0162/Balance Works/Banaskantha/BLOA-162 Date: 11-01-2023 DLOA Ref. NO. WR-II/C&M/SD/0162/Blance Works/Banaskantha/LOA-162 Date: 17-01-2023 SAP PO no. 6900011753 06 Months i.e. 11-01-2023 to 11-07-2023 | 2022-2023 | 2023-01-11 | 2023-03-30 | 2023-08-31 | 2026-01-10 | 2026-04-10 | Power Grid Corporation of India Limited 765/400 KV Sub-station, Village-Mudetha, Arnivada Road, Dist : Banaskantha (Gujrat) - 385530 | Manoj Kumar | Pankaj Kumar Gupta | Sr. Manager | DGM Asst Manager | 9420491809 | 9425409756 | pankajkumatgupta@powergrid.in | srsharma@powergrid.in | 5661457.9 | 18% | 58,61,603.53 | CPG Not Submitted | N/A | N/A | N/A | https://drive.google.com/file/d/1V74nsftnBOz9jJD85NbOEcpo5buoYh_4/view?usp=sharing | https://drive.google.com/file/d/1DRjOP3yVThdi_RS-QsSOTOmmURdAyz2d/view?usp=sharing | M/s SHRI TARA CHANDRA CHETTRI | SHRI TARA CHANDRA CHETTRI | 9800747637 | tara.namchi2099@gmail.com | 11AHUPC4767D3ZE | 0.1 | 12320100 | 2025-12-05 | https://drive.google.com/file/d/1dyuDcEXH-i4q7MsKCJ1OjepfJNFVjZHm/view?usp=share_link https://drive.google.com/file/d/1rvzvQYKiWGY7L0-uypwq6TATNvdSCh1A/view?usp=sharing | gsharma2060@yahoo.com | 89430 31000 | Mr. Rajeev Ranjan Mishra | 2025-11-18 | 2025-11-18
Ongoing | Specification No: SR1/NT/W-CIVIL/DOM/B00/23/01750/WC-3127/RFx-5002002710 | Tender fee online 2800/- | EMD - BG Form | received | ICICI | 10113 | Sheeba | IRAM | PGCIL | Andhra Pradesh | Vijayawada | Civil works package for conversion of Conventional C&R Panels to Bay Kiosk (SPR) based protection system at 400kV Vijayawada Substation under ADD-CAP 2019-24. | LOA Ref. No. SR-I/C&M/WC-3127/LOA-3215/2023/CNMO- 114013/023 Date: 06-07-2023, SAP PO No. 6400009830 12 Months i.e. 06-07-2023 to 06-07-2024 | 2022-2023 | 2023-07-06 | 2023-08-26 | 2024-07-06 | 2025-12-31 | NIL | POWER GRID CORPN. OF INDIA LTD. NUZVID ROAD, NUNNA POST VIJAYAWADA 400 KV SUBSTATION VIJAYAWADA - 521212, AP | Mr. Sanjay Chaki | Sh. K Nagamohana Rao | Asst Manager | Sr. GM, | 9337750052 | 9717296922 | sharmaabhishek@powergrid.in | sharmaabhishek@powergrid.in | 21779710 | 18% | NIL | BG Submitted | 3092267 | 2027-08-30 | 2027-04-15 | TERMINATE | https://drive.google.com/file/d/1MHuD3mBAMmBpPKeVVyEy9Ui8_2oOWVx_/view?usp=sharing | M/s BASUKI CONSTRUCTION | Mr. Rajeev Ranjan Mishra | 9006004031 | pcarajeev@gmail.com | 10AZLPM7685H1Z1 | 0.09 | 10113/12320113 | 2023-07-29 | https://drive.google.com/file/d/1O-Ojox9i867qNtrBn3IVmZLTezSIWJhT/view?usp=sharing | ysrana.aiepl@gmail.com | 8435422224 | GANESH SHARMA | 2024-11-15 | 2024-11-15
Ongoing | Specification No.: ODP/BB/C&M-3592/OT-26/RFx No. 5002003305/23-24 | Exempted | Exempted as per MSME bidder | Not received | HDFC | 10122 | Manpreet Kaur | IRAM | PGCIL | Odisha | Jaypore | Package: Construction of boundary wall for setting of one new Govt. Industrial Training Institute at Dharamgarh Sub division of Kalahandi District under POWERGRID, Odisha Projects. (Under CSR Budget). | LOA Ref. No. ODP/BB/C&M-3592/OT-26/LOA-56/24-25 Date: 06-06-2024 SAP Po no.: 4100006666 Six Months i.e. 06-06-2024 to 05-12-2024 | 2024-2025 | 2024-06-06 | 2024-02-02 | 2024-12-05 | 2026-01-31 | NIL | Power Grid Corporation of India Ltd. 400/220 KV Indravati Sub-Station ,PO: Mukhiguda, Dist: Kalahandi ,Odisha-766026. | Sh. K Nagamohana Rao | Mr. Sanjay Chaki | Sr. GM | DGM Chief Manager Engineer J.E. Civil` | 7724877834 | 09078883612 | skchakki@powergrid.in | sharmaabhishek@powergrid.in | 13755408 | 18% | NIL | CPG Not Submitted | N/A | N/A | N/A | https://drive.google.com/file/d/1Z4tj4MOOIchrtJoe0C2RjUnaEkeLKj5n/view?usp=sharing | https://drive.google.com/file/d/1MHuD3mBAMmBpPKeVVyEy9Ui8_2oOWVx_/view?usp=sharing | M/s JMB CONSTRUCTION | Mr. pramod kumar jena | 7978611952 | pramodjena02@gmail.com | 21AEOPJ8470M2Z0 | 10 | 10122-12420125 | 2025-09-16 | https://drive.google.com/file/d/1O-Ojox9i867qNtrBn3IVmZLTezSIWJhT/view?usp=sharing | heavensgarden10@gmail.com | 9494141498 | Arun Kumar MS | 2025-09-05 | 2025-09-05
Ongoing | SPECIFICATION NO.: NR3/NT/S-MISC/DOM/K00/24/08278, RFx: 5002003617 | Tender fee online 1500/- | Exempted as per MSME bidder | Not received | HDFC | 10124 | Sheeba | IRAM | PGCIL | Uttarpradesh | KANPUR (U.P) | Civil works for Retrofit of existing conventional control and protection system with new IEC 61850 based SAS at 400kV Kanpur Substation. | LOA Ref. No.: NR-II/C&M/KO0/2024/5002003617/400kV Kanpur/36629 dated 31.07.2024 SAP PO No.: 4100006458 8 (Eight) Months i.e. 31-07-2024 to 31-03-2025 | 2024-2025 | 2024-07-31 | 2024-10-05 | 2025-03-31 | 2025-12-31 | 2026-05-10 | Power Grid Corporation of India Limited 400/220 kV Sub-Station, Kalpi Road, Village-Bhauti, PO: Chakarpur, Dist: Kanpur- 209305 Uttar Pradesh | S.M. Pandey | S.M. Pandey | Sr. GM | DGM | 8003492932 | 8004910703 | sm.pandey@powergrid.in | sm.pandey@powergrid.in | ₹ 25,96,197.77 | 18% | NIL | CPG Not Submitted | N/A | N/A | N/A | https://drive.google.com/file/d/1lzKO-4Gyurc9VtR3Dq4iccSJXQUMwbv8/view?usp=sharing | https://drive.google.com/file/d/1nHFcui78oQfEKacrxaM8gMkDnbfD0MT4/view?usp=sharing | M/s RAGHAVAJIT CONSTRUCTION PRIVATE LIMITED | Mr. ARUN SINGH | 9532450230 | neerajknp8090@gmail.com | 09AANCR6103P1ZR | 0.1 | 03-10124-12420144 | 2025-01-18 | https://drive.google.com/file/d/1E5Gi3AycUyIBhDNzsETf9qJqX38VZOPr/view?usp=sharing | pcarajeev@gmail.com | 89430 31000 | Mr. Rajeev Ranjan Mishra | 2024-07-18 | 2024-07-18
Ongoing | SPECIFICATION NO.: NR3/NT/W-CIVIL/DOM/K00/24/08300 (RFx 5002003620) | Exempted | Exempted as per MSME bidder | received | SBI | 10125 | Manpreet Kaur | IRAM | PGCIL | Uttarpradesh | Allahabad | Part A Civil Works for 400/220 kV Allahabad Substation Extension (SS-119). | NOA Ref. No.: NR-IIIC&M/2024/5002003620/NOA/24-110460/01/36765 dt 16-08-2024 SAP PO 4100006492, 4100006493 06 Months i.e. 16-08-2024 to 15-02-2025 | 2024-2025 | 2024-08-16 | 2024-09-29 | 2025-02-15 | 2025-12-31 | NIL | Power Grid Corporation of India Limited 400kV Allahabad Sub-station Vill: Sarangapur, Post: Dandupur, Rewa Road, Prayagraj, Uttar Pradesh-211008 | Peeyush Pandey | Peeyush Pandey | DGM | (Sr. DGM) | 7381868892 | 8004912062 | peeyushpandey@powergrid.in | pallavi.mishra@powergrid.in | ₹ 3,08,22,670.00 | 18% | NIL | BG Submitted | ₹ 30,82,267.00 | 2026-05-15 | 2026-03-15 | https://drive.google.com/drive/folders/1nRhARy0Gzg_mdCIr7dQkvH-vYQGm3AeE | https://drive.google.com/file/d/1DcNxa7X_i_IZAe-Kd7eNzuYVMMZXHK9m/view?usp=sharing | M/s KABIR INFRA | Mr. FAKHRUL HASAN | 8757375705 | fakhrulhasan@kabirinfra.co.in | 10ABCFK4223G1Z0 | 4 | 02-10125-12520008 | 2025-06-18 | https://drive.google.com/file/d/1xXOP85996uETHAazzTmW1wYAA_FNJfbU/view?usp=sharing | heavensgarden10@gmail.com | 9494141498 | Mr. Rajeev Ranjan Mishra | 2025-05-10 | 2025-05-10
Ongoing | GEM/2024/B/5068478 Bidding Document Number: 9900282698 | Tender fee online 5000/- | Exempted as per MSME bidder | Not received | HDFC | 10127 | Manpreet Kaur | Monika Kochhar | NTPC | Maharashtra | Solapur | Biennial maintenance of Horticulture works of Township RLI Main plant area for the year 20242025 NTPC Solapur | Purchase Order No. : 4000343344-020-1041 Date : 30.09.2024 Contract No: GEMC-511687738285099 27/09/2024 | 2024-2025 | 30.09.2024 | 2024-10-05 | 2026-10-04 | 2026-12-04 | NIL | NTPC Limited 1045 Solapur STPP PO- HOTGI STATION SOUTH SOLAPUR, SOLAPUR Maharashtra-413215, India | Sheeja | Mr. Satish kolluri | Manager | Sr. Manager TAD Civil DGM O&M | 8917567285 | 94039 64663 | satishkolluri@ntpc.co.in | kkarora@ntpc.co.in; | 36757676.36 | 18% | NIL | CPG Not Submitted | N/A | N/A | N/A | https://drive.google.com/file/d/18Z7eyNlP_MNu3fQN1TRf6d94QopIcpWW/view?usp=sharing | https://drive.google.com/file/d/17f5agKAHz4o8luTIzT7BvItUwtwfoSrz/view?usp=sharing | M/s BRAJESH KUMAR ( WO not signed | Mr. BRAJESH KUMAR | 9412203436 | heavensgarden10@gmail.com | 09AIGPK2578M2ZN | 0.1 | 10127-12420131 | 2024-10-01 | https://drive.google.com/file/d/1IBaXnvGPPcoxlAogxEt6jyjNRs7gIDg0/view?usp=sharing | pcarajeev@gmail.com | 8757375705 | Mr. FAKHRUL HASAN | 2025-04-04 | 2025-04-04
Ongoing | Specification No(s): WR-1/C&M/VRL/NIT-116/I-3401-2024/Rfx-5002003643 | Tender fee online 500/- | EMD - BG Form | Not received | SBI | 10128 | Sheeba | IRAM | PGCIL | Chattisgarh | Raigarh | Horticulture Development of the main entrance area at HVDC-Raigarh. | NOA Ref No: WR-1/C&M/VRL/NIT-116/1-3401-2024/NOA-1427/984 dt 27-09-2024, SAP PO:6900013302 12 months i.e. 27-09-2024 to 27-09-2025 | 2024-2025 | 2024-09-27 | 2025-03-24 | 2025-09-27 | 2026-03-31 | 2026-06-10 | Power Grid Corporation of India Ltd, 11km Milstone, Nandeli Road, PO and Villege-Kotra, Distt- Raigarh-496001 (Chattisgarh) | Mr. Satish kolluri | Sheeja | Juniour Engineer | Ast Manager Civil | 9480486408 | 6379589014 | sheejas@powergrid.in | sumeetmishra@powergrid.in | ₹ 58,70,096.83 | 18% | NIL | BG Submitted | ₹ 58,70,09.683 | 2026-07-15 | 2026-05-15 | https://drive.google.com/file/d/1VnA9my8CBGzcuqt1yvGzJdj-U4-S0h8A/view?usp=sharing | https://drive.google.com/file/d/1bdpVrP-EXeziwcQXbUB3V_7OM5DRH98b/view?usp=sharing https://drive.google.com/file/d/1bQZZvd5K6NN7GRT80sU1fL89Rtdi5FhD/view?usp=sharing | M/s Shree Balaji Contractors & Suppliers | . Mr. SATVEER SINGH | 94168 93740 | satveersorout2425@gmail.com | 09ADVFS1708H1ZM | 8 | 10128-12420145 | 2025-01-23 | https://drive.google.com/file/d/1UkY_ValX24syCW8urN7z5aBPiqQLwd15/view?usp=sharing | gsharma2060@yahoo.com | 89430 31000 | Ms. Sangana Praveena | 2025-05-10 | 2025-05-10
Ongoing | Tender Reference Number NTPC/USSC-CPG1/9900282646 Tender ID 2024_NTPC_88104_1 | Exempted | Exempted as per MSME bidder | Not received | Axixs | 10129 | Manpreet Kaur | Monika Kochhar | NTPC | Telangana | Ramagundam | Transportation of Crushed coal between coal yards of RSTPS & TeSTPS and Internal transfer of uncrushed coal at TeSTPS by road. | Purchase Order No. : 4000342945-067-1041 Date : 27.09.2024 | 2024-2025 | 27.09.2024 | 01.11.2024 | 31.10.2025 | 30.04.2026 | NIL | NTPC Limited 1057 Telangana STPP Station PO JYOTINAGAR DISTRICT PEDDAPALLI Telangana-505215, India | Sh.Hemant B. Shinde | Sh.Hemant | Ast Manager Civil | AGM(FT) Sr. Manager | 82628 49044 | 9423192800 | hemantshinde@ntpc.co.in; | PUSHPAKASHYAP@NTPC.CO.IN | 14900000 | 18% | NIL | CPG Not Submitted | N/A | N/A | N/A | https://drive.google.com/file/d/1cVDey8TSaN3Z3fHiZ7f3eFxPJ4JFSaPb/view?usp=sharing | https://drive.google.com/file/d/1ew7mIAk9bof_fx_ARKxArQxCpXuWhJvB/view?usp=sharing | M/S DBS Contractores | Sunil Boora | 92542100000 | boorasunil290@gmail.com | 06ANTPB1091L1ZS | 0.12 | 10132-12420146 | 2024-10-04 | https://drive.google.com/file/d/1mvIRxRPQrnr0WXnsmVunGg3EU5ONdLRa/view?usp=sharing | pcarajeev@gmail.com | 9494141498 | Mr. Rajeev Ranjan Mishra | 2025-05-22 | 2025-05-22
Payment Pending | Specification No: SR-I/C&M/WC-3658/2024/RFx-5002003561 | Tender fee online 2700/- | EMD - DD Form | Not received | SBI | 10130 | Manpreet Kaur | IRAM | PGCIL | Aandhar Pradesh | Nellore | AMC-II for De-Weeding, Grass Cutting and Jungle Clearance at Nellore Pooling Station. | LOA Ref. No. : SR-1/C&M/WC-3658/LOA- 3898/2024 dt 30-09-2024 02 Years i.e. 30-09-2024 to 30-09-2026 | 2024-2025 | 2024-09-30 | 2025-03-02 | 2024-04-05 | 2025-03-30 | NIL | Power Grid Corporation of India Limited Nellore Pooling Station | Mr. Anil Kumar Arji | Mr. Anil Kumar Arji | Manager | JUNIOR ENGINEER (Civil), Chief Manager | 7420062581 | 8639940547 | anilkumararji@powergrid.in | sharmaabhishek@powergrid.in | ₹ 43,57,509/- | 18% | NIL | NA | N/A | N/A | N/A | https://drive.google.com/file/d/1ThrotMU2mRSgxPo3BYou-7Sed-A9YEAh/view?usp=sharing | https://drive.google.com/file/d/1ErpFESuJh2vWlXUgtYuJyQuD4Tu4_gZF/view?usp=sharing | M/S SANVITHA CONSTRUCTIONS | Ms. Sangana Praveena | 9494141498 | sanvithareddy2017@gmail.com | 37KRBPS8260L1ZX | 11 | 02-10130-12520010 | 2025-07-09 | https://drive.google.com/file/d/1RBCCNTLSLtSy26QatlCa6dQWEqMNIxd6/view?usp=sharing | gsharma2060@yahoo.com | 8435422224 | Arun Kumar MS | 2025-05-30 | 2025-05-30
Ongoing | Tender Reference Number NTPC/USSC-CPG1/9900288002 Tender ID 2024_NTPC_90365_1 | Exempted | Exempted as per MSME bidder | received | Axixs | 10131 | Manpreet Kaur | Monika Kochhar | NTPC | Uttarpradesh | Dadri | BIENNIAL CONTRACT FOR UPKEEPING AND OPERATIONAL SUPPORT FOR CHP STAGE-2 1 | Purchase Order No. : 4000345110-042-1041 Date : 24.10.2024 ( version : 1 Date : 29.10.2024 Ref. No.: LOI - 1041-042- 24/10/2024 | 2024-2025 | 2024-10-24 | 01.12.2024 | 2025-03-30 | 30--01-2026 | NIL | NTPC Limited 1011 National Capital Power Project P.O. VIDYUT NAGAR DADRI GAUTAM BUDH NAGAR(U.P.) Uttar Pradesh-201008 India | Mr. Pramod Kumar | Mr. Pramod Kumar | AGM(FT) Sr. Manager | DGM DGM(FM) Sr. Manager (CHP-OPN) AGM(FM) | 9896406543 | 9424141520 9650966991 | pramodkumar01@ntpc.co.in | ANILGUPTA03@NTPC.CO.IN | 43401900.96 | 18% | NIL | CPG Not Submitted | N/A | N/A | N/A | https://drive.google.com/file/d/1M7l70RFevk6hwyd09HlGlvGHx_n7uX0U/view?usp=sharing | https://drive.google.com/file/d/1OrdjsuYsw70WWVSVtxdrgKVra3M4qOS-/view?usp=sharing | AEC | Ms. Sangana Praveena | 9494141498 | sanvithareddy2017@gmail.com | 23AIVPD0911G1ZM | 11 | 02-10130-12520010 | 2025-07-09 | https://drive.google.com/file/d/1O-Ojox9i867qNtrBn3IVmZLTezSIWJhT/view?usp=sharing | pcarajeev@gmail.com | 9494141498 | Arun Kumar MS | 2025-06-18 | 2025-07-03
Ongoing | SPECIFICATION NO: WR2/NT/W-CIVIL/DOM/G01/24/03062 | Tender fee online 3000/- | EMD - DD Form | Not received | HDFC | 10132 | Sheeba | IRAM | PGCIL | Gujarat | BHUJ | Landscaping Work at 765/400/220KV Bhuj Pooling Sub-Station. | BLOA Ref. No. WR=II/C&M/E-883519/RKS/24-25/BLOA-421 date: 26-10-2024 05 Months i.e 26-10-2024 to 25-03-2025 | 2024-2025 | 2024-10-26 | 2024-12-15 | 2025-03-25 | 2025-12-31 | 2026-05-28 | Power Grid Corporation of India Limited Survey No.152/1,Village-Pallanpur (Badi) ,Taluka Nakhatarana, District- Kutch (Gujarat) | Shripad Waman Kolte | Bahadur Singh Meena | Engineer | Junior Engineer DGM | 9896406543 | 8432765577 | bahadurmeena@powergrid.in | rksingh41610@powergrid.in | 5555500.37 | 18% | NIL | CPG Not Submitted | N/A | NA | NA | https://drive.google.com/file/d/1DaAYkNezqu2sLluAF-QitUS8PW2bLhFL/view?usp=sharing | https://drive.google.com/file/d/1l-I291tjhimPFZsJzjEId2kCKwJ6shcw/view?usp=sharing | M/s DEVSHRDDHA CONSTRUCTION | Mr. Dev Singh | 9494141498 | sanvithareddy2017@gmail.com | 24ALQPG5095G1ZV | 0.02 | 10132-12420146 | 2025-01-28 | https://drive.google.com/file/d/1qWoe5xhtc9V9BcVdHmWaLZeYwEBzJqVQ/view?usp=sharing | gsharma2060@yahoo.com | 89430 31000 | GANESH SHARMA | 2024-10-01 | 2025-05-22
Ongoing | Specification No(s): NIT Ref.: WR-I/C&M/VRL/NIT-195/I-3567-2024/RFX-5002003847 | Tender fee online 4000/- | EMD - DD Form | Not received | Axixs | 10135 | Manpreet Kaur | IRAM | PGCIL | Maharashtra | Wardha | Painting of Office Buildings and Boundary Wall of Ss & Ts at 765/400/220 KV Wardha Substation. | Ref No.: WR-I/C&M/VRL/NIT-195/I-3567-2024/NOA-1579/1389 दिनाक: 13.12.2024, SAP PO NO. 5100054698 08 months 13-12-2024 to 12-08-2025 | 2024-2025 | 2024-12-13 | 2024-08-12 | 2025-08-12 | 2026-02-28 | NIL | PowerGrid Corporation of India Ltd. , Plot No. D-1 , MIDC Area , Deoli , Distt-Wardha-442 101 – Maharastra Sh. Shripad Waman Kolte | Mr.Kaushal Kumar | Mr.Kaushal Kumar | Engineer | J.E Sr. DGM | 9425409785 | 7352969020 | swkolte@powergrid.in | vijayrlikhar@powergrid.in | 2888691.92 | 18% | NIL | CPG Not Submitted | N/A | N/A | NA | https://drive.google.com/file/d/1UIrlwwXhU4AMmdgtyJhbXzsylyvsJeRH/view?usp=sharing | https://drive.google.com/file/d/1l-I291tjhimPFZsJzjEId2kCKwJ6shcw/view?usp=sharing | M/s Rajavat Interiors Construction & Traders | Mr. Dev Singh | 9826339996 | rajavatinteriors@gmail.com | 23AIVPD0911G1ZM | 0.12 | 03-10135-12420149 | 2025-02-12 | https://drive.google.com/file/d/1VKqGOzgE_bpJV7X_-yTunfT84TUdnIF-/view?usp=sharing | heavensgarden10@gmail.com | 8435422224 | Ms. Sangana Praveena | 2025-01-23 | 2025-05-30
Ongoing | SPECIFICATION NO: WR2/NT/W-CIVIL/DOM/G01/24/13864, RFx Number 5006005726 | Exempted | EMD - BG Form | received | Axixs | 10136 | Manpreet Kaur | IRAM | PGCIL | Bihar | Boisar | Civil Works Pertaining Augmentation of Transformation Capacity at 400/220 kV Boisar Sub-Station in Maharashtra by 400/220 kV, 1x500 MVA (5th) ICT. | NOA REF. No.: WR-II/C&M/E 865224/NV/24-25/LOA-601 Date 22-01-2025 & LOA Ref. No.: WR-II/C&M/E 865224/NV/24-25/LOA-601 Date 29-01-2025. 05 Months i.e. 22-01-2025 to 22-06-2025 | 2024-2025 | 2025-01-22 | 2023-04-23 | 2025-06-22 | 2025-12-31 | NIL | Power Grid Corporation of India Limited 400/220 kv Boisar Substation, | Rajnikant Agrawal | Shrirang Moreshwar Vartak | Manager | Sr. Deputy General Manager | 9423072643 | 9429893652 | shrirang@powergrid.in | cnmwr2@powergrid.in | 25895391 | 18% | NIL | BG Submitted | 2589539.1 | 2026-03-15 | 2026-01-15 | https://drive.google.com/file/d/15clFOzr0X-49oux8fBQZSKlq5IRCRhI4/view?usp=sharing https://drive.google.com/file/d/13u29QSOtwPuHT3JA7-fiaWeVsTvTMGOU/view?usp=sharing | https://drive.google.com/file/d/1diFjjQSUaEAGN93lg6Sw5g-Vj8Ikbf0d/view?usp=sharing | M/s COCHIN ENGINEERING PROJECTS INDIA PRIVATE LIMTED | Mr. UmeshM Manickan | 89430 31000 | info.cepipl@gmail.com | 32AALCC7219F1ZT | 0.05 | 01-10136-12420148 | 07/02/2025 | https://drive.google.com/file/d/1ffN6JGqoJCIRF-LiA6IZv0ClrFTG6PVQ/view?usp=sharing | manager.cst@railway.com | 89430 31000 | Mr. Rajeev Ranjan Mishra | 2024-10-04 | 2025-07-03
Ongoing | SPECIFICATION NO.: NR3/NT/W-CIVIL/DOM/K00/24/14070 (RFx 5002003962) | Tender fee online 4000/- | EMD - NEFT/ RTGS Form | received | SBI | 10137 | Manpreet Kaur | IRAM | PGCIL | Uttarpradesh | Orai | Site Package A2 (Civil Works) for Extension of 765 kV Orai substation (Shifting & conversion of 765kV fixed line reactor to bus reactor) under Western Region Expansion Scheme XXXIII (WRES-XXXIII): Part C1. | DLOA Ref No: NR-III/C&M/2025/5002003962/LOA/25-101188/01, date:29-01-2025 9 Months i.e 29-01-2025 to 29-10-2025 | 2024-2025 | 2025-01-29 | 2025-04-14 | 2025-10-29 | 2026-01-31 | 2026-09-28 | Power Grid Corporation of India Limited 765/400 kv Orai Substation Distt. Jalaun | Shrirang Moreshwar Vartak | Rajnikant Agrawal | AGM(FT) Sr. Manager | Sr. DGM | 9797860055 | 7895000703 | rkagarwal@powergrid.in | pallavi.mishra@powergrid.in | 15402645.16 | 18% | NIL | NA | N/A | NA | NA | https://drive.google.com/file/d/1lXcuU3WVhryL_TH10GfdWx4I1KRW6Aun/view?usp=sharing | https://drive.google.com/file/d/1l-I291tjhimPFZsJzjEId2kCKwJ6shcw/view?usp=sharing | M/s HARI SHIV SHAKTI STONE CRUSHING COMPANY | Mr. Vinay Sirohi | 7055225111 | vinaysirohi05@gmail.com | 23AAKFH0514N1ZH | 5 | 03-10137-12520012 | 2025-07-25 | https://drive.google.com/file/d/19-W98CIZUuQr-W3sogdOoghF2uWRP3oU/view?usp=sharing | pcarajeev@gmail.com | 8757375705 | Arun Kumar MS | 2025-07-09 | Arun Kumar MS
Ongoing | Tender Ref No.: N2JM/C&M/CS/57(24), RFX. 5006005505 | Tender fee online 3500/- | EMD - BG Form | received | Axixs | 10138 | Manpreet Kaur | IRAM | PGCIL | Ladakh | Drass, Kargil & Khalsti | Construction of approach road for closed store buildings at Drass, Kargil & Khalsti Substations and Patrolling Path at Drass & Kargil Substations. | SAP PO Ref. No. 4100006691 dt:28-02-2025, NOA : 4000005936 3 MONTHS i.e. 28/02/2025 to 27-05-2025 | 2024-2025 | 2025-02-28 | 2023-05-27 | 2025-05-27 | 2026-07-31 | NIL | Power Grid Corporation of India Limited, Drass Sub Station 194102, Rampur. | Mr.Kaushal Kumar | Sh Arshad Iqbal Shah | Sr Manager | Sr. GM | 9986050347 | 9797860055 | arshadiqbal@powergrid.in | azeemdrabu@powergrid.in | 3448869.51 | 18% | NIL | BG Submitted | 2,92,277/- | 2027-03-15 | 2027-01-15 | https://drive.google.com/file/d/11T7C593CgbW2qWgHhgwnAppAjfbAqgQr/view?usp=sharing | NA As In vol - I (03 Section-III BDS Volume-I CS-57(24)) Clause No. ITB 34 , point 65 (page No. 22 & 23) | King Construction & Builders | Md. Khalid / Md. Gani | 1835425649136 | kingconstructions1@gmail.com | 01AAVPW5940N1ZW | 6 | 02-10139-12520016 | 2025-07-09 | https://drive.google.com/file/d/1wRkXbEyOqv6aAauaE1wtOy0oZjm46_48/view?usp=sharing https://drive.google.com/file/d/1jtZeDydt0FKQApmUZaotyTqahJ8wakeN/view?usp=sharing | heavensgarden10@gmail.com | 9494141498 | Mr. UmeshM Manickan | 2025-07-09 | 2025-05-30
Ongoing | Tender Reference Number: 03/000011/2025 Tender ID: 2025_BEL_96893_1 | Tender fee online 4500/- | EMD - DD Form | received | HDFC | 10139 | Sheeba | IRAM | BEL | Tamil Nadu | Chennai | Infrastructure Facilities for Aero Hub at Sriperumbudur (Chennai) Tamil Nadu. | LOI Ref No: 03/000011/2025 dt: 26-04-2025 4 Months after 14 days of issuance of LOI i.e. 10-05-2025 to 09-09-2025 Site Clearence Mail Received on dt 04-06-2025 So time duration shall be 04-06-2025 to 04-10-2025 | 2024-2025 | 2025-04-26 | 2025-05-10 | 2025-09-09 | 2026-02-04 | NIL | Bharat Electronics Limited VWQC+JMG Sirukalathur, Tamil Nadu. | Bahadur Singh Meena | Arvind Singh | Manager | DY.MANAGER(PMG-1/ES) | 9797860055 | 080-22195115 | arvindsinghs@bel.co.in | pc.ewdtf@bel.co.in | 22670468.26 | 18% | NIL | NA | N/A | N/A | NA | https://drive.google.com/file/d/16lhKuQuffJ_LK2zMOJyyQiVpLCuBh_B6/view?usp=sharing | https://drive.google.com/file/d/15_7IvfEKA0rwHIXARa6YxZYWcnwNqBo_/view?usp=sharing | M/s SASMI INFRA & CO | Mr. VEERARAGAVAN SURYA | 9626917866 | sasmi.infra18@gmail.com | 33IKKPS7376R2ZS | 0.1 | 02-10139-12520016 | 2025-08-20 | WO Cancelled | gsharma2060@yahoo.com | 89430 31000 | Mr. MOHAMMAD FAIJAN | 2025-01-28 | 2022-05-14
Ongoing | GEM/2025/B/5972293 NTPC/USSC–CPG1/9900297556 | Exempted | Exempted as per MSME bidder | received | Axixs | 10140 | Manpreet Kaur | Monika Kochhar | NTPC | Bihar | Barh | Manual Unloading of Coal from BOXN/ BOXNHL and BOBR/ BOBRN Rakes at Track Hopper, NTPC Barh. | Purchase Order No. : 4000359253-064-1041 Date : 29.04.2025 Contract No: GEMC-511687743490213 | 2025-2027 | 29.04.2025 | 2025-05-12 | 2026-05-11 | 2027-05-11 | NIL | NTPC Limited 1028 Barh Super Thermal Power Project P.O. BARH BARH PATNA Bihar-803213, India | Arvind Singh | Salil Kr. Pandey | Sr Manager | AGM engineer | 7368807203 | 8004942641 | SALILKUMARPANDEY@NTPC.CO.IN | BHUPESHGUPTA@NTPC.CO.IN | 31159506.78 | 18% | NIL | NA | N/A | N/A | N/A | https://drive.google.com/file/d/13TU3UF8bPzTn8xKL2KaSJNqXpQ_u8zBl/view?usp=sharing | https://drive.google.com/file/d/15mbOgZjvfo3rn78GnfVPbXChwg6LeFGA/view?usp=sharing | M/s MAGADHEERA CONSTRUCTION | Mr. Ravi Shankar Vidyarthi | 9153217419 | vidyarthi1991@gmail.com | 10BOGPD7641D1ZK | 6 | 01-10142-12520019 | 2025-05-10 | https://drive.google.com/file/d/1wRkXbEyOqv6aAauaE1wtOy0oZjm46_48/view?usp=sharing https://drive.google.com/file/d/1jtZeDydt0FKQApmUZaotyTqahJ8wakeN/view?usp=sharing | heavensgarden10@gmail.com | 9494141498 | Ms. Sangana Praveena | 2022-04-05 | 2022-04-05
Ongoing | SPECIFICATION NO.: NR2/NT/W-CIVIL/DOM/J01/25/12796 RFX: 5002004786 | Tender fee online 2650/- | EMD - NEFT/ RTGS Form | received | SBI | 10141 | Manpreet Kaur | IRAM | PGCIL | Jammu (J&K) | Samba | Facelifting/Civil Renovation of IDBI vacated Ground floor portion of RHQ Building for RTAMC Upgradation project. (Package-1). | BLOA No.: N2JM/C&M/CS/251(25)/BLOA/25-112339 Date: 13-10-2025 3 Months i.e. 13-10-2025 to 12-01-2026 | 2025-2026 | 2025-10-13 | 2025-11-10 | 2026-01-12 | 2026-04-12 | NIL | M/s Power Grid Corporation of India Limited ESG Department. Office Block no. 26, Rail Head Complex Jammu-180012. | Vijay Prakash Jarwal | Ms. Sudharma | AGM(FT) Sr. Manager | [DGM(C&M)] | 9149469200 | 7368807203 | sharmaabhishek@powergrid.in | sharmaabhishek@powergrid.in | 11266485.29 | 18% | NIL | CPG Not Submitted | N/A | N/A | NA | https://drive.google.com/file/d/1GmD_ry5EBAQN_STGiqRffwiwf0kJ-8Ty/view?usp=sharing | https://drive.google.com/file/d/15mbOgZjvfo3rn78GnfVPbXChwg6LeFGA/view?usp=sharing | M/s MAGADHEERA CONSTRUCTION | Mr. Ravi Shankar Vidyarthi | 9494141498 | sanvithareddy2017@gmail.com | 10BOGPD7641D1ZK | 11 | 02-10139-12520016 | 2025-05-10 | https://drive.google.com/file/d/1wRkXbEyOqv6aAauaE1wtOy0oZjm46_48/view?usp=sharing https://drive.google.com/file/d/1jtZeDydt0FKQApmUZaotyTqahJ8wakeN/view?usp=sharing | pcarajeev@gmail.com | 8757375705 | Mr. Rajeev Ranjan Mishra | 2022-05-14 | 2022-05-14
Ongoing | Specification No.: NR1/T/W-CIVIL/DOM/I00/25/05458 – RFx Number 5002004419 | Exempted | EMD - DD Form | Not received | Axixs | 10142 | Manpreet Kaur | IRAM | PGCIL | Rajasthan | Jaipur | Construction of Closed Store, Open Store, Oil Shed & Watchtowers at 765/400 kV Dausa Substation | NOA Ref. No.: RP/JP/C&M/25-26/OT/SRM/NOA/25-112530 Date: 03.11.2025 Four (04) Months i.e. 03-11-2025 to 02-03-2026 | 2025-2026 | 2025-11-03 | 2024-03-02 | 2026-03-02 | 2026-05-02 | 2026-01-28 | M/s Power Grid Beawar Dausa Transmission Limited Power Grid Corporation of India Limited Rajasthan Project Office, Jaipur (Rajasthan) | Salil Kr. Pandey | Vijay Prakash Jarwal | AGM(FT) Sr. Manager | [DGM(C&M)] | 9435555368 | 9149469200 | vijayprakashjarwal@powergrid.in | sharmaabhishek@powergrid.in | 20864320.69 | 18% | NIL | CPG Not Submitted | N/A | N/A | NA | https://drive.google.com/file/d/1Ryz__nT99fzF9nPGUCIXYkstD4abWI94/view?usp=sharing | https://drive.google.com/file/d/15mbOgZjvfo3rn78GnfVPbXChwg6LeFGA/view?usp=sharing | M/s VS Aditya Buildcon | Mr. Vinay Sirohi | 7055225111 | vinaysirohi05@gmail.com | 09CKZPS7305F2ZE | 5 | 01-10142-12520019 | 2025-11-18 | mail on 24-11-2025 | gsharma2060@yahoo.com | 8757375705 | Arun Kumar MS | 2025-07-19 | 2025-07-19
Completed | SPECIFICATION NO: NESH/CSM/SRM/OT/5000-03, Rfx. 5002001796 | Tender fee online 3500/- | EMD - NEFT/ RTGS Form | Not received | HDFC | 20022 | Sheeba | IRAM | PGCIL | Assam | Misa | Construction of Hi-tech Class-Cum Conference Room at Misa EDC at Misa Sub -Station. | vide NOA Ref. No. NESH/CSM/FY:2021-22/5000-23/NOA/149 dt 23-12-2021.” SAP P.O. Number : 6800009930 version : 1 Date : 19.09.2022 | 2021-22 | 2021-12-23 | 2022-03-22 | 2022-06-23 | 2026-01-31 | NIL | Power Grid Corporation of India Limited 400/220 kV Misa Sub-station, Village: Veluguri, Pin-782427 Dist: Hojai, Assam. | Sh. Praveen Kumar T V S, | Navin Kumar Mahato | DGM | Ch. Manager (I/C) Chief Manager | 9436175830 | 9099995703 | mrinmoymajumder97@powergrid.in | sharmaabhishek@powergrid.in | 11704211 | 18% | 12795811 | CPG Not Submitted | NA | NA | NA | https://drive.google.com/drive/folders/1yEmUdKIvJBzoASMapkD1sS3NkVKr4Adr?usp=sharing | https://drive.google.com/file/d/1f0_0rCLnm4Xig2mOzMpgmTuARBOyBm08/view?usp=sharing | M/S AR INFRATECH | ANJU SINGH | 8130529991 | raj1977.singh@gmail.com | 09OBZPS8680E1Z8 | 0.1 | 02-20022-224240 | 2024-11-15 | https://drive.google.com/file/d/1tFl-Pu37A3BNNobG7MDaHjP0KFJhxvL_/view?usp=sharing | gsharma2060@yahoo.com | 8435422224 | Ms. Sangana Praveena | 2025-07-08 | 2025-07-08
Ongoing | Specification No(s): WR-I/C&M/SYE/I-2022/NIT-82/2023/Rfx- 5002002731 | Tender fee online 4000/- | EMD - NEFT/ RTGS Form | Not received | Axixs | 20036 | Manpreet Kaur | IRAM | PGCIL | Chattisgarh | Raigarh | “Construction of 2nos. of Outdoor Covered store buildings at POWER GRID, HVDC, Raigarh Station.” | BLOA Ref. No. WR-I/C&M/SYE/NIT-82/2022-23/Rfx/LOA-816/704 Date 26-09-2023 09 Months 26-09-2023 to 26-06-2024 | 2023-2024 | 2023-09-26 | 2023-03-23 | 2024-12-26 | 2026-02-28 | NIL | Power Grid Corporation of India Ltd, 11Km Milestone Nandeli Road, Village and PO: Kotra, Distt: Raigarh - 496001, (Chhattisgarh) | MADHURJYA KAKATI | Sh. Praveen Kumar T V S, | Sr Manager | Engineers-In-Charge | 9436302823 | 8023093783 | sharmaabhishek@powergrid.in | sheejas@powergrid.in | 13036492 | 18% | NIL | CPG Not Submitted | N/A | N/A | NA | https://drive.google.com/file/d/15c61paAgeI1sJ7YGBplu8tzhn5QsIkEB/view?usp=sharing | https://drive.google.com/file/d/1UFL-jCtCFAvDwenEFWzqp8PR0G6000t_/view?usp=sharing | M/s PERFECT DESIGNING HUB | Mr. MOHAMMAD FAIJAN | 7869091028 | pdh.tech.consulttancy@gmail.com | 22ACCPF4621Q1ZQ | 05 | 02-20036-224248 | 2025-09-05 | https://drive.google.com/file/d/18kTgiilTwM7kkXwLC5EytbuMB1_LJ79f/view?usp=sharing | heavensgarden10@gmail.com | 9494141498 | GANESH SHARMA | 2022-08-08 | 2022-08-08
Ongoing | NIT NO. : 9900264848/026/1019 Dated 12.09.2023 | Tender fee online 3000/- | Exempted as per MSME bidder | Not received | Axixs | 20037 | Manpreet Kaur | Monika Kochhar | NTPC | Odisha | Darlipalli | Construction of toilet units along with drinking water facilities at different location at plant area of NTPC- Darlipali. | Purchase Order No. : 5500043565-026-1019 Date : 28.11.2023 EMD online payment | 2023-2024 | 2023-11-28 | 2022-03-22 | 2022-06-23 | 2026-01-31 | NIL | NTPC Limited 1053 Darlipali STPP P.O. Darlipali Odisha Sundargarh Odisha-770072, India | Navin Kumar Mahato | Kaushik Banerjee | Manager | Sr. Manager AGM Engineers-In-Charge | 9435560613 | 9435587000 | kaushikbanerjee@ntpc.co.in; | manishkumar01@ntpc.co.in | 8030237.67 | 18% | 803023.767 | NA | N/A | N/A | NA | https://drive.google.com/file/d/1hcMrYZ0T0o1G4Zm1qbPO11n54nZ7tfxh/view?usp=sharing | https://drive.google.com/file/d/1sLccB2M23nLhIqgofyRnE1HrTBXroYtM/view?usp=sharing | M/s Shri Shyam Baba Infratech | AVINASH KEDIA | 8827955000 | gsharma2060@yahoo.com | 22BODPK0495R1ZK | 0.06 | 20037-224237 | 2024-07-18 | https://drive.google.com/file/d/1fUEHOOnJtoPh0cBmOwaoL3tcj6qAAHdF/view?usp=sharing | pcarajeev@gmail.com | 8757375705 | Ms. Sangana Praveena | 2025-12-05 | 2025-12-05
Completed | Specification No.: ODP/BB/C&M-3428/OT-15/RFx No. 5002002975/23-24 | Exempted | EMD - NEFT/ RTGS Form | received | HDFC | 20039 | Manpreet Kaur | IRAM | PGCIL | Odisha | Jeypore | Package: Demolishing Existing Foundations, Excavation, and construction of New 500 MVA Transformer & other required equipment Foundation, and disposal of malba/unserviceable waste at POWERGRID, Jeypore Sub-Station (Under ADD-CAP 2019-24)”. | LOA Ref. No. : ODP/BB/C&M-3428/OT-15/LOA-210/23-24 dt 14-02-2024 SAP PO: 4100006109 02 Months i.e 14-02-2024 to 14-04-2024 | 2023-2024 | 2024-02-14 | 2023-05-15 | 2024-04-14 | 2025-12-31 | 2026-07-28 | Power Grid Corporation of India Ltd., 400/220KV Jeypore Sub-Station PO- Kaliagaon, Jeypore, Odisha | MR. Pankaj Singh | Siva Behara | AGM(FT) Sr. Manager | Dy. Manager | 96509 99820 | 9052331230 | siva5313@powergrid.in | cnmodisha@powergrid.in | 7413479 | 18% | NIL | CPG Not Submitted | 741348 | N/A | NA | https://drive.google.com/file/d/1PXO4v5Aqz6aVIbQYrUrfnXu887oxFq9W/view?usp=drive_link | https://drive.google.com/file/d/1gs86QyT5hmWiHCjS2A0iAxpWDdFURfiT/view?usp=sharing | AIEPL | AVINASH KEDIA | 9494141498 | sanvithareddy2017@gmail.com | 10BOGPD7641D1ZK | 11 | 01-10142-12520019 | 2025-05-10 | https://drive.google.com/file/d/1wRkXbEyOqv6aAauaE1wtOy0oZjm46_48/view?usp=sharing https://drive.google.com/file/d/1jtZeDydt0FKQApmUZaotyTqahJ8wakeN/view?usp=sharing | pcarajeev@gmail.com | 8757375705 | Arun Kumar MS | 2025-06-18 | 2023-07-29
Ongoing | Tender Ref No. : NTPC/USSC-CPG2/9900284682 Tender ID : 2024_NTPC_88844_1 | Tender fee online 500/- | Exempted as per MSME bidder | Not received | HDFC | 20043 | Sheeba | Monika Kochhar | NTPC | Bihar | Kanti | CONSTRUCTION OF CISF BARRACK AT KALWARI, NTPC – KANTI. | Purchase Order No. : 5500045392-025-1019 Date : 30.09.2024 ( Purchase Order No. : 5500045392-025-1019 Date : 30.09.2024 ( version : 1 Date : 02.05.2025 ) | 2024-2025 | 30.09.2024 | 2024-10-16 | 2025-04-15 | 2026-03-31 | NIL | NTPC Limited 1087 Muzaffarpur Thermal Power Station PO Kanti, Distt. Muzaffarpur Muzaffarpur Bihar-843130, India | Siva Behara, | Vikash Kumar Jaiswal | AGM(FT) Sr. Manager | DGM (Civil) CCD DGM AGM(P) | 80049 47089 | 9425178449 | VKJAISWAL03@NTPC.CO.IN | anujsharma@ntpc.co.in | 4389743.15 | 18% | NIL | NA | N/A | N/A | NA | https://drive.google.com/file/d/183aQ6wVSPQFjDA6bAz3TChRX8Cxg3zJF/view?usp=sharing | https://drive.google.com/file/d/1G8UeYXt2ltLuLp9GVAAPBLtEM3ACdTdj/view?usp=sharing | M/S RITIKA ENGICON PRIVATE LIMITED | Ritesh Kumar | 9113166835 | guptaritesh517@gmail.com | 10AANCR7697G1ZY | 8.5 | 02-20043-12520003 | 2025-04-04 | https://drive.google.com/file/d/1a4R752VRroui7zHIU1EkCx5ggpcCMuoh/view?usp=sharing | gsharma2060@yahoo.com | 8435422224 | GANESH SHARMA | 2024-10-01 | 2025-09-16
Ongoing | GEM/2024/B/5177254 NTPC/USSC–CPG1/9900284701 | Exempted | Exempted as per MSME bidder | received | HDFC | 20044 | Manpreet Kaur | Monika Kochhar | NTPC | Uttarpradesh | Dadri | BIENNIAL CONTRACT FOR UPKEEPING AND OPERATIONAL SUPPORT FOR CHP STAGE1 AT NTPC DADRI | Purchase Order No. : 4000344790-042-1041 Date : 22.10.2024 अनुबंध 􀀐मांक¦Contract No: GEMC-511687708136821 अनुबंध 􀀢त􀀢थ¦Contract Generated Date : 22-Oct-2024 बोली/आरए/पीबीपी सं􀀳या¦Bid/RA/PBP No.: GEM/2024/B/5177254 | 2024-2025 | 22.10.2024 | 2024-12-01 | 2026-11-30 | 2026-12-30 | NIL | NTPC Limited 1011 National Capital Power Project P.O. VIDYUT NAGAR DADRI GAUTAM BUDH NAGAR Uttar Pradesh-201008-India | Kaushik Banerjee | BHARAT VARUN | Manager | Sr. Manager (CHP-OPN) AGM(FM) DGM(FM) DGM (FM) | 9650966991 | 9896406543 | BHARATVARUN@NTPC.CO.IN | SONAMJHA@NTPC.CO.IN | 38892860.68 | 18% | NIL | CPG Not Submitted | N/A | N/A | NA | https://drive.google.com/file/d/13nRDx3OxCNmSoWwLQov69Qu-bpmiODvi/view?usp=sharing | https://drive.google.com/file/d/1mPce5sIocWqh9Zc4QEWLwSpgdQdsKjyy/view?usp=sharing | AIEPL | Ritesh Kumar | 9494141498 | sanvithareddy2017@gmail.com | 10BOGPD7641D1ZK | 0.1 | 01-10142-12520019 | 2025-05-10 | https://drive.google.com/file/d/1wRkXbEyOqv6aAauaE1wtOy0oZjm46_48/view?usp=sharing https://drive.google.com/file/d/1jtZeDydt0FKQApmUZaotyTqahJ8wakeN/view?usp=sharing | manager.cst@railway.com | 89430 31000 | Mr. UmeshM Manickan | 2025-01-23 | 2025-01-18
Completed | Tender Specification No.: NR1/NT/W-MISC/DOM/I00/24/08478 (Rfx: 5002003651) | Tender fee online 5000/- | EMD - NEFT/ RTGS Form | received | HDFC | 20045 | Manpreet Kaur | IRAM | PGCIL | Uttarakhand | Kashipur | Construction of Revetment wall for the tower foundation protection work at tower location number 134 in 400KV D/C Kashipur-Roorkee Transmission Line. | NOA Ref. No. : N1/C&M/24-25/AM/OT/1363/NOA Date: 14-11-2024 i.e. 14-11-2024 to 14-01-2025 | 2024-2025 | 2024-11-14 | 2024-04-15 | 2025-01-14 | 2025-12-15 | 2026-02-28 | Power Grid Corporation of India Limited 134/400 KV Kashipur, Roorkee- Dehradun Road, Puhana, Roorkee, Haridwar, Uttrakhand-247667. | Sh Priya Ranjan Kumar | Mr. Ajay Thakur | Engineer | Engineer Junior Engineer (Civil) | 9431215266 | 9805200187 | ajay.kumar1@powergrid.in | praveen.kumar26@powergrid.in | 3277240 | 18% | NIL | CPG Not Submitted | N/A | N/A | NA | https://drive.google.com/file/d/1DC0U3icgNW7iFaeuGM8omChE6Cc8i4NE/view?usp=sharing | https://drive.google.com/file/d/1UeJdr6tVWCefkeIkwqCtfdaTLAOAvhjE/view?usp=sharing https://drive.google.com/file/d/1lSoLGIu9JizQxKd5p7RkvFBYE3DDS4rn/view?usp=sharing | M/s HARI SHIV SHAKTI STONE CRUSHING COMPANY | Mr. VINAY SIROHI | 7055225111 | vinaysirohi05@gmail.com | 23AAKFH0514N1ZH | 5 | 02-20045-224245 | 2025-05-22 | https://drive.google.com/file/d/1JpK9ekQCSIz_6mRvnSz2Tt6ol0XQ9uQ6/view?usp=sharing | heavensgarden10@gmail.com | 8757375705 | Arun Kumar MS | 2024-10-04 | 2025-06-18
Ongoing | Limited tender Tender Reference Number NTPC/USSC-CPG2/9900297331 Tender ID 2025_NTPC_94507_1 | Exempted | Exempted as per MSME bidder | received | SBI | 20046 | Manpreet Kaur | Monika Kochhar | NTPC | Bihar | Kanti | Misc. Civil Works in MTPS Township | Purchase Order No. : 4000360024-020-1019 Date : 22.05.2025 ( version : 0 ) EMD online payment | 2025-2026 | 2025-05-22 | 2025-05-25 | 2026-02-24 | 2026-04-24 | NIL | NTPC Limited 1087 Muzaffarpur Thermal Power Station PO Kanti, Distt. Muzaffarpur Muzaffarpur Bihar-843130, India | Sh Pramod Kumar | Shri H. K. Sinha, | AGM(FT) Sr. Manager | DGM | 8218180331 | 7369000241 | HKSINHA@NTPC.CO.IN | SOMNATHMODAK@NTPC.CO.IN | 11905720.17 | 18% | NIL | NA | N/A | N/A | NA | https://drive.google.com/drive/folders/1jUKHeHn_YfiohZU9ikZjZlriPRApLJIE?usp=drive_link | https://drive.google.com/file/d/1SpYLTKYfd5AGqInAstjBVH0AycXYXWAV/view?usp=sharing https://drive.google.com/file/d/1dOaiTinS0jFZ0-8bcPo8amzHIw2khXqj/view?usp=sharing | M/S RITIKA ENGICON PRIVATE LIMITED | Ritesh Kumar | 9113166835 | guptaritesh517@gmail.com | 10AANCR7697G1ZY | 0.1 | 01-20046-224246 | 2025-05-30 | https://drive.google.com/file/d/1j_xIohEeUlDd_0Jyxut500g-Ao2N6Qjd/view?usp=sharing | manager.cst@railway.com | 8435422224 | Arun Kumar MS | 2025-11-18 | 2024-10-01
Completed | Bid No.: GEM/2025/B/6230044 | Exempted | Exempted as per MSME bidder | received | HDFC | 20047 | Sheeba | Monika Kochhar | NTPC | Bihar | Kanti | Biennial Maintenance of Horticulture work inside MTPS Township | Purchase Order No. : 4000363186-020-1041 Date : 24.06.2025 Contract No: GEMC-511687760325072 | 2025-2026 | 2025-06-24 | 2025-07-19 | 2027-07-18 | 2027-05-18 | NIL | NTPC Limited 1087 Muzaffarpur Thermal Power Station PO Kanti, Distt. Muzaffarpur Muzaffarpur Bihar-843130, India | Sh Satish Chandra Verma | Shri H. K. Sinha, | AGM(FT) Sr. Manager | DGM | 9424141520 | 7369000241 | HKSINHA@NTPC.CO.IN | SOMNATHMODAK@NTPC.CO.IN | 11812714.45 | 18% | NIL | NA | N/A | N/A | NA | https://drive.google.com/file/d/1vPq7jG2gZtrW_Cwl6Tzkuk9CydEacMGH/view?usp=sharing | https://drive.google.com/file/d/1mPce5sIocWqh9Zc4QEWLwSpgdQdsKjyy/view?usp=sharing | M/s VISHAL ENTERPRISES | Mr. RAJNISH KUMAR | 95349 22111 | vishalenterpriseskanti@gmail.com | 10DPAPK8867R1Z8 | 0.09 | 01-20047-224247 | 2025-07-03 | https://drive.google.com/file/d/13stcdOsgda51pukjlN4O0mvAvD3m2vxT/view?usp=sharing | gsharma2060@yahoo.com | 8757375705 | Mr. UmeshM Manickan | 2024-11-15 | 2025-01-23